## Goals by Week 5
Week 5 Goals
Characters
3 Fully animated characters
All interactions (including faction specific) implemented
Majority of models/textures complete
Player movement/physics finalised (possibly standardised across levels)
Levels
Fully implemented
"Fun"
Majority of models/textures complete
Time limits well adjusted
Programming
All primary level/character scripts implemented
No fatal bugs
Few to no non-fatal bugs
Ready for external testing

## Weekly Dev Plan
Game Component | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Area Focus | Prototype Touch-Ups |  | Tutorial Carriage | The Ancients Carriage | Industrialists | External Testing
Art |  |  | Models, Texture & Animations | Models, Texture & Animations | Models, Texture & Animations | Respond to testing
Levels |  |  | Base Level Design | Base Level Design | Base Level Design
Mechanics | Unity Project "Cleaning" (sorting assets etc) | Further Camera Implementation (Multi Camera) | Implementation | Implementation | Implementation

## Backlog
Assets | File Name/Location | Team Member Responsible | Date Due (Week) | Predicted Duration (Hours) | Complete? (1 = yes/0 = no) | Notes | Tasks Complete by Due Date
Universal | [6 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
Adventurer Prefab | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Prefabs\Player\Factions\Adventurer.prefab | Ashleigh/Pierce | 2 | 4 | 1 |  | 2 | 6 | 7 | 12 | 1
Ancient Prefab | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Prefabs\Player\Factions\Ancient.prefab | Ashleigh/Pierce | 2 | 4 | 1 |  | Total Hours per week
Industrialist Prefab | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Prefabs\Player\Factions\Industrialist.prefab | Ashleigh/Pierce | 2 | 4 | 1 |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
Audio Manager | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Prefabs\UI\AudioManager.prefab | Pierce | 1 | 3 | 1 |  | 6 | 25 | 22 | 60 | 6
Character Animations | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Animations | Ashleigh/Pierce | 2 | 5 | 1 |  | Remaining Effort (hours)
HUD/GUI | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Prefabs\UI | Nathan/Ashleigh | 1 | 3 | 1 |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
Industrialist Prefab | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Prefabs\Player\Factions\Industrialist.prefab | Ashleigh/Pierce | 2 | 4 | 1 |  | 144 | 119 | 97 | 37 | 31
Player Movement Script | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Scripts\Player\P_Movement.cs | Nathan/Pierce/Josh | 4 | 5 | 1 | Dependant on complexity of movement in each carriage | Hours Completed by Due Date
Background (+ script) | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Materials\Scenery\Background | Ashleigh/Nathan/Pierce | 5 | 3 | 1 |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
| GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Scripts\Scene |  |  |  | 1 |  | 6 | 25 | 22 | 35 | 3
Train Tracks |  | All | 5 | 3 | 0 |  | Hours Completed per week
[7 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
[7 empty] | 6 | 31 | 91
Tutorial | [6 empty] | Actual Progress
Level Model - Industrial Section |  | Ashleigh | 4 | 4 | 0 |  | 144 | 113 | 22
Level Model - Adventurer Section |  | Ashleigh | 4 | 4 | 0
Level Model - Ancients Section |  | Ashleigh | 4 | 4 | 0
Adventurers Mechanic Script | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Scripts\Player\P_Gshot.cs | Josh | 4 | 4 | 1
Industrialist Mechanic Script | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Scripts\Interactable\IN_ProximityLight | Josh | 4 | 3 | 1
The Ancients Mechanic Script | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Scripts\Interactable\IN_Pyramid_Door | Nathan | 4 | 2 | 1
Lever |  | Nathan/Josh/Pierce/Feng | 4 | 1 | 0
Pressure Plate |  | Nathan/Josh/Pierce/Feng | 4 | 1 | 0
Weight |  | Nathan/Josh/Pierce/Feng | 4 | 1 | 0
The Ancients Carriage
Collapsible Platform | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Prefabs\Interactables\CollapsiblePlatform.prefab | Ashleigh/Nathan | 3 | 3 | 1
Level Model | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Mesh\Scenery\Pyramid Scene.fbx | Ashleigh | 2 | 4 | 1
Lever | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Prefabs\Interactables\Lever.prefab | Ashleigh/Nathan | 3 | 3 | 1
Pressure Plate | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Prefabs\Interactables\Pressureplate.prefab | Ashleigh/Nathan | 3 | 3 | 1
Push Pin Spike Hazard | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Prefabs\Interactables\Push_Pin_Trap.prefab | Ashleigh/Nathan | 3 | 3 | 1
Regular Platforms | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Prefabs\Scene Objects\PyramidPlatform.prefab | Ashleigh/Nathan | 3 | 4 | 1
The Ancients Mechanic - Pyramid Door | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Prefabs\Interactables\PyramidDoor.prefab | Ashleigh/Nathan | 3 | 3 | 1
The Ancients Mechanic - Script | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Scripts\Interactable\IN_Pyramid_Door | Nathan/Feng | 3 | 3 | 1
Industrialist Carriage
Level Model |  | Ashleigh | 4 | 4 | 0
Industrialist Mechanic - Script | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Scripts\Interactable\IN_ProximityLight | Josh | 4 | 3 | 1
Industrialist Mechanic - Proximity Lights | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Prefabs\Interactables\ProximityLight.prefab | Josh | 4 | 3 | 1
Weight | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Prefabs\Interactables\weight.prefab | Nathan | 4 | 2 | 1
Lever |  | Ashleigh/Nathan | 4 | 3 | 0 | Currently using The Ancients Level Model
Pressure Plate |  | Ashleigh/Nathan | 4 | 3 | 0 | Currently using The Ancients Level Model
Platforms/Walls (Static) | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Prefabs\Scene Objects\IndustrialistPlatform.prefab | Ashleigh/Nathan | 4 | 4 | 1 | Tedious placement may affect completion time
| GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Prefabs\Scene Objects\IndustrialistWall.prefab |  |  |  | 1
Vertical/Horizontal Moving Sections | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Scripts\Scene\Industrial_HorizontalSlider.cs | Nathan | 4 | 3 | 1
| GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Scripts\Interactable\IN_VerticalSlider.cs |  |  |  | 1
Lantern Script | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Scripts\Interactable\IN_Lantern.cs | Josh | 4 | 2 | 1
Puzzle Indicator Lights Script | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Scripts\Interactable\IN_IndicatorLight.cs | Nathan | 4 | 2 | 1
Industrial Brake Script | GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Scripts\Interactable\IN_Industrial_Brake.cs | Nathan | 4 | 2 | 1
| GitHub\There-are-no-brakes\There are no brakes\Assets\There are no Brakes\Scripts\Interactable\IN_Industrial_Brake_Activated.cs |  |  |  | 1