## Week Five Goals
Week 5 Goals
Three Characters
1 Protagonist - Human
2 Antagonists - One Wizard, One Troll
2 Levels
Dwarf Mine
Open Scene
4 Weapons
…
…
…

## Asset List
Assets | File Name | Team Member Responsible | Date Due
Human Protagonist - Name:Aaron
Concept Art Front/Side/Face | UnityPath/model/AaronConc.png | Steven | Week 3
Mesh | UnityPath/model/AaronMesh.obj | Jenny | Week 3
Rig | UnityPath/model/AaronRig.3ds | Jenny | Week 3
Texture | UnityPath/model/AaronTextAtlas.png | Steven | Week 3
Animations
Walk Anim | UnityPath/model/AaronWalk.anim | George | Week 3
Idle Anim | UnityPath/model/AaronIdle.anim | George | Week 3
Leap Anim | UnityPath/model/AaronLeap.anim | George | Week 3
Attack Anim | UnityPath/model/AaronAttack.anim | George | Week 3
Audio
Weapon Grunt | UnityPath/audio/AaronGrunt.wav | Fred | Week 3
Yell | UnityPath/audio/AaronYell.wav | Fred | Week 3
Death Cry | UnityPath/audio/AaronDeath.wav | Fred | Week 3
…
…
…

## Weekly Dev Plan
Game Component | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
Art |  | 1st Protagonist Complete | 1st Antagonist Complete | 2nd Antagonist Complete
Levels |  | Ist Level Draft | 1st Level Complete | 2nd Level Darft | 2nd Level Complete
Mechanic |  | Grapple Mechanic | … | … | …
…
…

## Daily Plan Monday Week 2
Monday 04/03/13 | Artist - Steven | Software Eng - Georgina | Modeller - Jenny | …
Hour 1 | Complet Aaron Art Front | Grapple code complete | Complete Barn Model in Dwarf Mine level | …
Hour 2 | … | … | … | …
Hour 3 | … | … | … | …
Hour 4 | … | … | …
Hour 5 | Complete - Aaron Elevation Complete | Testing Grapple | Complete Barn Texture uvs in Dwarf Mine level
Hour 6 | … | … | …
Hour 7 | … | … | …
Hour 8 | Upload Repo | Upload Repo | Upload to Repo
Tuesday 05/03/13 | Artist - Steven | Software Eng - Georgina | Modeller - Jenny
Hour 1 | Complete - Aaron Texture | … | Draft Aaron Mesh - Mudbox - depends on Steven's concept art
Hour 2 | … | … | …
Hour 3 | … | … | …
Hour 4 | … | … | …
Hour 5 | Complet - UV Map Aaron Texture | … | Complete - UV Map Aaron Texture with Steven
Hour 6 | … | … | …
Hour 7 | … | … | Aaron Mesh - Decimation and Normal Map Generation
Hour 8 | Upload Repo | … | Upload to Repo