## Goals by Week 5
Week 5 Goals
Characters
3 Fully animated characters
All interactions (including faction specific) implemented
Majority of models/textures complete
Player movement/physics finalised (possibly standardised across levels)
Levels
Fully implemented
"Fun"
Majority of models/textures complete
Time limits well adjusted
Programming
All primary level/character scripts implemented
No fatal bugs
Few to no non-fatal bugs
Ready for external testing

## Weekly Dev Plan
Game Component | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Area Focus | Prototype Touch-Ups |  | Tutorial Carriage | The Ancients Carriage | Industrialists | External Testing
Art |  |  | Models, Texture & Animations | Models, Texture & Animations | Models, Texture & Animations | Respond to testing
Levels | Week 3: Base Level Design; Week 4: Base Level Design; Week 5: Base Level Design
Mechanics | Unity Project "Cleaning" (sorting assets etc) | Further Camera Implementation (Multi Camera) | Implementation | Implementation | Implementation

## Backlog
Assets | File Name | Team Member Responsible | Date Due
Human Protagonist - Name:Aaron
Concept Art Front/Side/Face | UnityPath/model/AaronConc.png | Steven | Week 3
Mesh | UnityPath/model/AaronMesh.obj | Jenny | Week 3
Rig | UnityPath/model/AaronRig.3ds | Jenny | Week 3
Texture | UnityPath/model/AaronTextAtlas.png | Steven | Week 3
Animations
Walk Anim | UnityPath/model/AaronWalk.anim | George | Week 3
Idle Anim | UnityPath/model/AaronIdle.anim | George | Week 3
Leap Anim | UnityPath/model/AaronLeap.anim | George | Week 3
Attack Anim | UnityPath/model/AaronAttack.anim | George | Week 3
Audio
Weapon Grunt | UnityPath/audio/AaronGrunt.wav | Fred | Week 3
Yell | UnityPath/audio/AaronYell.wav | Fred | Week 3
Death Cry | UnityPath/audio/AaronDeath.wav | Fred | Week 3